## Executive Gantt
Alation to In-House: Business Data Catalog - Gantt Chart
Data governance catalog migration — requirements, design, build, testing, cutover (program timeline; launch target Sep 16, 2027)
Sources: Product Brief — Alation to In-house (Mar 2026) · BDC Feature Inventory Matrix (PRD F01–F35). Mitigate contract risk via extension / parallel run per brief.
ID | Phase | Workstream / deliverable | Start | End | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | 2027-08-30 | 2027-09-06 | 2027-09-13 | 2027-09-20 | 2027-09-27 | 2027-10-04 | 2027-10-11 | 2027-10-18 | 2027-10-25
0 | Intake | Kickoff & program intake (T+0 milestone 4/30/26) | 2026-04-27 | 2026-05-08
1 | Phase 1 | Requirements — current use, enhancements, OMS leverage & gaps | 2026-07-01 | 2026-08-25
1a | Phase 1 | Consolidated requirements doc & gate sign-off | 2026-08-18 | 2026-08-28
2 | Design | Solution design — backend (data model, integrations, lineage, APIs) | 2026-08-26 | 2026-10-16
2b | Design | Solution design — frontend / BDC UX (search, glossary, asset IA) | 2026-09-14 | 2026-11-03
2c | Design | Migration design (extract–transform–load, validation strategy) | 2026-10-07 | 2026-11-03
2d | Design | Architecture / design review & approval | 2026-10-27 | 2026-11-03
3 | Build | Development — MVP parity (high-priority catalog: F01–F06, F09–F11, F16, F20–F21, F23–F25, F30, F33) | 2026-11-04 | 2027-03-31
3b | Build | Development — Phase 2 (medium: bulk edit, dataflows, domains, exports, usage, API, policy, etc.) | 2027-01-04 | 2027-06-15
3c | Build | Development — migration tooling, parallel-run hooks, hardening | 2027-04-01 | 2027-06-30
4 | Quality | Test planning, automation & regression prep | 2027-06-01 | 2027-06-30
4b | Quality | Formal testing window (4 weeks, July 2027) | 2027-07-01 | 2027-07-28
5 | Cutover | Migration execution, UAT, stabilization (6 weeks) | 2027-07-29 | 2027-09-11
6 | Adoption | Change management — training, champions, comms calendar | 2027-06-01 | 2027-09-15
6b | Cutover | Go-live readiness, cutover rehearsal, launch | 2027-09-04 | 2027-09-16
7 | Hypercare | Post-launch stabilization (optional window) | 2027-09-16 | 2027-10-16
Legend: each timeline column is one calendar week (Monday–Sunday). Bar shading shows the activity span. Color key identifies workstream type.
Workstream color key
Kickoff / intake
Requirements
Design
Development / build
Testing / QA
Migration / UAT
Change / adoption
Launch

## Milestones & dates
Milestone checkpoints — Business Data Catalog migration
Alation to In-House · Dates per program plan
Milestone | Target date | Notes
Kickoff / intake (T+0) | 2026-04-30 | Program start; align DSS / OMS / stakeholders
Phase 1 requirements complete | 2026-08-28 | 8-week window Jul–Aug 2026 (per plan)
Design complete | 2026-11-03 | 10-week backend + frontend design Aug–Nov
Development window | 2026-11-04 | 8 months through Jun 2027 (MVP → parity → tooling)
Formal testing | 2027-07-01 | 4-week test window (July 2027)
Migration + UAT + stabilization | 2027-07-29 | 6-week execution ending ahead of launch
Launch — Internal Solution primary | 2027-09-16 | Go-live; Alation decommission per contract

## Feature matrix (summary)
BDC Feature Inventory — priority snapshot for migration waves
See full matrix in Google Doc · High items = MVP wave
# | Feature | Priority | MVP wave | Primary users | PRD
1 | Search & Discovery | High | MVP | DPMs, PMs, Analysts, Stewards | F01
2 | Business Glossary | High | MVP | DPMs, PMs, Analysts, Stewards | F02
3 | Catalog Browse | High | MVP | DPMs, PMs, Analysts, Stewards | F03
4 | Table / asset detail & descriptions | High | MVP | DPMs, PMs, Analysts, Stewards | F04
5 | Recommendations (AI metadata) | High | MVP | Stewards | F16
6 | Flags (endorse / warn / deprecate) | High | MVP | DPMs, PMs, Analysts, Stewards | F21
7 | Data Lineage | High | MVP | DPMs, Engineers, … | F05
8 | Admin analytics dashboard | High | MVP | Admin | F25
9 | Tags & classification | High | MVP | Governance, DPMs, Stewards | F06
10 | Expanded data sources | High | MVP | Admins | F30
11 | Product pages (authoring) | High | MVP | PMs, DPMs, Stewards | F33
12 | Data sources & connectors | High | MVP | DPMs, Engineers | F11
13 | Authentication / SSO | High | MVP | All users | F20
14 | Folders / source navigation | High | MVP | Cross-functional | F23
15 | Ownership / stewardship | High | MVP | Admin | F09
Medium / Phase 2 examples | Bulk edit, dataflows, domains, exports, usage metrics, AI chat, catalog sets, dictionary import/export, saved queries, overview & social, custom fields, comments, version control, policy center, …