## Feature Build Gantt
Business Data Catalog — Feature Build Gantt
Roadmap: 2027 ¦ Kickoff Jun 1, 2026 · Launch May 1, 2027 · 41 weeks program ¦ Team: OMS (Madhuri + 4) + BDC (4 eng)
Sources: Data Catalog deck (1OdzAIMxb2gE4n36-8UoYhWXWg-4nzVF4m3i8V9XWYRw) · Business Data Catalog Feature Inventory Matrix (Mar 2026) · P1: Search, Glossary, Browse, Detail, API/migration · P2: Stewardship, Access, Flags
ID | Phase | Priority | Feature / deliverable | PRD | Start | End | time axis 2026-06-01 to 2027-05-10
— | Program & Governance | — | ▸ PROGRAM PHASE: Requirements gathering (8 wks · Q2–Q3 FY26) | — | 2026-06-01 | 2026-07-26
R1 | Requirements | All | Feature inventory validation & stakeholder interviews (matrix sign-off) | Doc | 2026-06-01 | 2026-06-28
R2 | Requirements | All | Persona stories & acceptance criteria (consumer, steward, compliance) | Intake | 2026-06-08 | 2026-07-12
R3 | Requirements | All | OMS capability mapping, gap analysis & migration field mapping | Brief | 2026-06-15 | 2026-07-19
R4 | Requirements | All | Consolidated requirements package & governance gate | — | 2026-07-13 | 2026-07-26
— | Program & Governance | — | ▸ PROGRAM PHASE: Solution design — backend + frontend (10 wks · Q3 FY26) | — | 2026-08-03 | 2026-10-11
D0 | Design & Architecture | All | Business Data Catalog shell, IA & OMS handoff patterns (Open in OMS, role-aware nav) | F30 | 2026-08-03 | 2026-09-06
— | Program & Governance | — | ▸ PROGRAM PHASE: MVP development (13 wks · Q3–Q4 FY26 → Q1 FY27) | — | 2026-10-12 | 2027-01-10
F01 | Design & Architecture | P1 | Search & Discovery — UX, filters, semantic/keyword search API contract | F01 | 2026-08-10 | 2026-09-20
F01 | Build — MVP (P1) | P1 | Search & Discovery — global search, AI-assisted results, natural language | F01 | 2026-10-12 | 2026-11-15
F02 | Design & Architecture | P1 | Business Glossary — term model, BU folders, synonym & stewardship UX | F02 | 2026-08-17 | 2026-09-27
F02 | Build — MVP (P1) | P1 | Business Glossary — browse, search terms, link to catalog assets, RBAC | F02 | 2026-10-19 | 2026-12-06
F03 | Design & Architecture | P1 | Catalog Browse — datasource → schema → table hierarchy & navigation | F03 | 2026-08-24 | 2026-10-04
F03 | Build — MVP (P1) | P1 | Catalog Browse — hierarchical explore, asset-type filters | F03 | 2026-10-12 | 2026-11-22
F04 | Design & Architecture | P1 | Asset Detail / Descriptions — table & column detail, owners, classifications | F04 | 2026-09-01 | 2026-10-11
F04 | Build — MVP (P1) | P1 | Asset Detail / Descriptions — business + technical fields, provenance badges | F04 | 2026-11-03 | 2026-12-20
F14 | Design & Architecture | P1 | API & integrations — read API, migration bulk ops, BI tool hooks | F14 | 2026-09-08 | 2026-10-11
F14 | Build — MVP (P1) | P1 | API integrations for migration — Alation extract, OMS load, validation jobs | F14 | 2026-11-17 | 2027-01-10
F09 | Design & Architecture | P2 | Ownership / Stewardship — assign owners, stewards, escalation paths | F09 | 2026-09-15 | 2026-10-11
F09 | Build — MVP (P2) | P2 | Ownership / Stewardship — thin endorse/reconcile in Business Data Catalog | F09 | 2026-12-01 | 2027-01-03
AC | Design & Architecture | P2 | Access Controls — feature-based permission postures (glossary, metrics, audit) | RBAC | 2026-09-22 | 2026-10-11
AC | Build — MVP (P2) | P2 | Access Controls — role-aware views & admin policy configuration | RBAC | 2026-12-08 | 2027-01-10
F21 | Design & Architecture | P2 | Flags — endorsements, warnings, deprecations, popularity signals | F21 | 2026-09-29 | 2026-10-11
F21 | Build — MVP (P2) | P2 | Flags — trusted / deprecated / warning badges on asset surfaces | F21 | 2026-12-15 | 2027-01-10
F16 | Build — MVP (P1) | MVP | Asset detail automation — AI description suggestions (human endorsement gate) | F16 | 2026-12-01 | 2027-01-10
F06 | Build — MVP (P2) | High | Tags & Classification — read filters; tag assignment where OMS supports edit | F06 | 2026-11-24 | 2027-01-10
F23 | Build — MVP (P1) | MVP | Folders / source navigation — article hierarchy & content organization | F23 | 2026-11-10 | 2026-12-27
F05 | Build — OMS leverage | MVP | Data Lineage — deep link & embed from OMS (table / column level) | F05 | 2026-10-26 | 2026-12-06
F20 | Build — OMS leverage | MVP | Authentication / SSO — enterprise SSO & role integration (OMS baseline) | F20 | 2026-10-12 | 2026-11-01
F11 | Build — OMS leverage | MVP | Data Sources & Connectors — critical datasource coverage via OMS / 626 | F11 | 2026-10-19 | 2026-12-13
DD | Build — MVP (P1) | MVP | Data Dictionary — steward workflows, privacy tags, CDE surfacing | DD | 2026-11-17 | 2027-01-10
— | Program & Governance | — | ▸ PROGRAM PHASE: Testing (4 wks · Q1 FY27) | — | 2027-01-11 | 2027-02-07
T1 | Testing & QA | All | Feature QA — P1 discovery flows (search, browse, glossary, detail) | P1 | 2027-01-11 | 2027-01-24
T2 | Testing & QA | All | Feature QA — P2 governance signals (stewardship, flags, access) | P2 | 2027-01-18 | 2027-02-07
T3 | Testing & QA | All | Regression, migration validation & performance testing | — | 2027-01-25 | 2027-02-07
— | Program & Governance | — | ▸ PROGRAM PHASE: Migration + UAT + stabilization (6 wks · Q1–Q2 FY27) | — | 2027-03-01 | 2027-04-11
M1 | Migration | All | Alation → OMS metadata load — glossary, articles, endorsements, tags | F14 | 2027-03-01 | 2027-03-21
M2 | Migration | All | Parallel run & steward UAT — link integrity, search parity checks | — | 2027-03-15 | 2027-04-04
M3 | Migration | All | Stabilization, defect burn-down & cutover readiness | — | 2027-03-29 | 2027-04-11
— | Program & Governance | — | ▸ LAUNCH — Business Data Catalog go-live | — | 2027-05-01 | 2027-05-01
Legend: weekly columns (Mon–Sun). Bar colors match Business-Data-Catalog-Migration-Executive-Gantt phases. Design rows precede build rows per feature. Regenerate: python3 meetings-tracker/generate_navigator_feature_gantt.py
Phase color key
Program & Governance
Requirements
Design & Architecture
Build — MVP (P1)
Build — MVP (P2)
Build — OMS leverage
Testing & QA
Migration
Cutover & Close

## Milestones
Business Data Catalog — program milestones
Milestone | Date | Notes
Kickoff | 2026-06-01 | Program start · Jun 1, 2026
Requirements complete | 2026-07-26 | 8 weeks · Q2–Q3 FY26
Solution design complete | 2026-10-11 | 10 weeks · Q3 FY26 (backend + frontend)
MVP development complete | 2027-01-10 | 13 weeks · Oct 2026 – Jan 2027
Testing complete | 2027-02-07 | 4 weeks · Jan–Feb 2027
Migration + UAT complete | 2027-04-11 | 6 weeks · Mar–Apr 2027
Launch — Business Data Catalog | 2027-05-01 | May 1, 2027

## Feature scope
Business Data Catalog Feature Inventory — scope snapshot
Wave | PRD | Feature | Priority | Primary use | Source
P1 | F01 | Search & Discovery | MVP | Find data assets across catalog | Deck + matrix #1
P1 | F02 | Business Glossary | MVP | Terms, definitions, BU organization | Deck + matrix #2
P1 | F03 | Catalog Browse | MVP | Datasource → schema → table hierarchy | Deck + matrix #4
P1 | F04 | Asset Detail / Descriptions | MVP | Table & column context, owners, tags | Deck + matrix #5
P1 | F14 | API & migration integrations | MVP | Bulk ops, Alation→OMS load | Deck P1
P2 | F09 | Ownership / Stewardship | MVP | Assign owners & stewards | Deck + matrix #12
P2 | — | Access Controls | MVP | Feature-based permission postures | Deck P2 + matrix #13
P2 | F21 | Flags | MVP/High | Endorse, warn, deprecate, popularity | Deck + matrix #7
— | F16 | Asset detail automation | MVP | AI suggestions, human endorsement | Matrix #6
— | F06 | Tags & Classification | High | PII/domain tags, filters | Matrix #16
— | F05 | Data Lineage | MVP | OMS leverage — deep link | Matrix #8
— | F20 | Authentication / SSO | MVP | OMS baseline | Matrix #10
— | F11 | Data Sources & Connectors | MVP | Critical datasource coverage | Matrix #9
— | F23 | Folders / source navigation | MVP | Article & content hierarchy | Matrix #11
— | DD | Data Dictionary | MVP | Steward workflows, CDEs | Matrix #3
Phase 2 | F25 | Admin analytics dashboard | High | Usage telemetry & reporting | Matrix #14
Phase 2 | F30 | Expanded data sources | High | 626 connectors beyond Snowflake | Matrix #17
Phase 2 | F33 | Product pages (authoring) | High | Product home, metrics links | Matrix #18