## Executive Gantt
Business Data Catalog — In-House (OMS) & Alation Migration ¦ Disney Streaming Services ¦ Executive Program Gantt
Sources: Product Brief & Migration Project Plan (Mar 2026) • Baseline Alation contract end: 1-Oct-2026 • Recommended: extension + cutover Feb–Mar 2027 • Decommission Oct 2027
Phase legend (timeline bar colors): | Program & Governance |  |  | Requirements |  |  | Design & Architecture |  |  | Build — MVP |  |  | Build — Full parity |  |  | Migration |  |  | Change & Training |  |  | Cutover & Close |  |  | Risk / Dependency
WBS | Phase | Workstream | Task / Deliverable | Owner | Start | End | Duration (wks) | % Complete | Status | Dependencies / Notes | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Sep-27 | Oct-27
1.0 | Program & Governance | Steering | Program kickoff, charter, steering committee cadence | Sponsor / PMO | 2026-03-01 | 2026-03-21 | 2 | 0% | Not started | Exec sponsor; cross-functional steering (Eng, Gov, Analytics)
1.1 | Program & Governance | Governance | RACI, governance charter — OMS as system of record | Data Governance | 2026-03-10 | 2026-04-04 | 3 | 0% | Not started | Phase-gate sign-off model
1.2 | Risk / Dependency | Vendor | Alation contract extension negotiation (target 1yr to Oct 2027) | Procurement / Sponsor | 2026-03-01 | 2026-05-15 | 10 | 0% | Not started | Fallback: 6-mo extension; wind-down / read-only pricing
1.3 | Program & Governance | Comms | Stakeholder comms plan & leadership reporting | PMO | 2026-03-15 | 2027-03-31 | 54 | 0% | Not started | Timeline visibility; change management
2.0 | Requirements | Current state | Feature inventory matrix & Alation metadata export | BA / Gov | 2026-03-15 | 2026-04-18 | 4 | 0% | Not started | API/MCP export; glossary, articles, tags, lineage, custom fields
2.1 | Requirements | Current state | Persona–feature matrix, stakeholder interviews, workflow docs | BA / Gov | 2026-03-22 | 2026-04-25 | 4 | 0% | Not started | Stewards, analysts, engineers, compliance, leadership
2.2 | Requirements | Evidence | Screenshot library (Alation + OMS) with annotations | BA / Gov | 2026-04-01 | 2026-05-02 | 4 | 0% | Not started | Side-by-side gap evidence for executives
2.3 | Requirements | Enhancements | Enhancement backlog — 'promised never delivered' + wishes | BA / Gov | 2026-04-08 | 2026-05-09 | 4 | 0% | Not started | Separate from MVP parity; Phase 2/3
2.4 | Requirements | OMS leverage | OMS capability matrix & requirements→OMS mapping | BA / OMS liaison | 2026-04-15 | 2026-05-16 | 4 | 0% | Not started | Align to Disney OMS roadmap
2.5 | Requirements | Gaps | Prioritized gap matrix & build scope (H/M/L criticality) | BA / Gov | 2026-04-22 | 2026-05-23 | 4 | 0% | Not started | MVP = critical business metadata parity
2.6 | Requirements | Sign-off | Consolidated requirements package & governance sign-off | Data Governance | 2026-05-10 | 2026-05-30 | 2 | 0% | Not started | Gate before detailed design
3.0 | Design & Architecture | Architecture | Target data model — glossary, tags, custom fields, stewardship | Architect / OMS | 2026-06-01 | 2026-06-28 | 3 | 0% | Not started | Business metadata in OMS
3.1 | Design & Architecture | Integration | Integration design — ingestion, lineage, APIs, Airflow links | Eng / OMS | 2026-06-08 | 2026-07-12 | 4 | 0% | Not started | Population of 'Not Available' fields where applicable
3.2 | Design & Architecture | UX | UI/UX design (OMS design system) — search, glossary, detail pages | UX / OMS | 2026-06-15 | 2026-07-19 | 4 | 0% | Not started | Discovery & stewardship flows
3.3 | Design & Architecture | Migration | Migration design — ETL mapping Alation→OMS, validation approach | Eng | 2026-06-22 | 2026-07-26 | 4 | 0% | Not started | Metadata-first; ≥95% preservation target
3.4 | Design & Architecture | Sign-off | Architecture & design review — approved for build | Steering | 2026-07-20 | 2026-07-31 | 1 | 0% | Not started | Formal gate
4.0 | Build — MVP | Core | OMS MVP: glossary & business metadata model (implement) | OMS / DSS Eng | 2026-06-15 | 2026-08-30 | 10 | 0% | Not started | Terms, definitions, stewardship
4.1 | Build — MVP | Discovery | OMS MVP: business-context search & discovery | OMS / DSS Eng | 2026-07-01 | 2026-09-13 | 10 | 0% | Not started | Glossary, articles, catalog objects
4.2 | Build — MVP | Metadata | OMS MVP: documentation, business description, tags on assets | OMS / DSS Eng | 2026-07-15 | 2026-09-27 | 10 | 0% | Not started | Populate placeholders
4.3 | Build — MVP | Lineage | OMS MVP: lineage depth + Airflow DAG/task link population | OMS / DSS Eng | 2026-08-01 | 2026-10-04 | 9 | 0% | Not started | Table/column per roadmap
4.4 | Build — MVP | Usage | OMS MVP: usage metrics (last access, top users) where supported | OMS / DSS Eng | 2026-08-15 | 2026-10-11 | 8 | 0% | Not started | Ownership / created-by fields
4.5 | Build — MVP | QA | MVP UAT, hardening, performance — governance acceptance | Gov / QA | 2026-09-15 | 2026-10-18 | 4 | 0% | Not started | Success metrics baseline
5.0 | Build — Full parity | Workflows | Full parity: custom fields, governance workflows, policy/compliance UI | OMS / DSS Eng | 2026-10-15 | 2027-01-15 | 13 | 0% | Not started | Policy center analog; integrations
6.0 | Migration | Planning | Migration runbook, environments, rollback, validation checkpoints | Eng / PMO | 2026-07-01 | 2026-08-15 | 6 | 0% | Not started | Industry: 3–6 mo execution window
6.1 | Migration | Extract | Build/run extraction — Alation (glossary, articles, tags, lineage, CF) | Eng | 2026-08-01 | 2026-09-30 | 8 | 0% | Not started | Secure export before contract risk
6.2 | Migration | Transform | Transform & map to OMS schema; reconciliation tooling | Eng | 2026-09-01 | 2026-11-15 | 10 | 0% | Not started | Data fidelity > speed
6.3 | Migration | Parallel run | Parallel run — Alation + OMS (user validation) | PMO / Gov | 2026-10-01 | 2027-01-15 | 15 | 0% | Not started | Reduces incident risk vs big-bang
6.4 | Migration | Load | Phased load to OMS, validation reports, lineage checks | Eng / Gov | 2026-11-01 | 2027-02-15 | 15 | 0% | Not started | ≥95% business metadata preserved
7.0 | Change & Training | Materials | Training curriculum, quick guides, videos, FAQs (vs Alation) | Gov / BA | 2026-12-01 | 2027-01-31 | 8 | 0% | Not started | Role-based: stewards, analysts, gov, engineers
7.1 | Change & Training | Delivery | Workshops, champions program, office hours (2–4 wk post cutover) | Gov | 2027-01-15 | 2027-03-15 | 8 | 0% | Not started | Adoption metrics; survey loop
8.0 | Cutover & Close | Cutover | Production cutover — OMS primary; Alation read-only | Steering / Eng | 2027-02-15 | 2027-03-15 | 4 | 0% | Not started | Rollback plan documented
8.1 | Cutover & Close | Milestone | MILESTONE: Alation baseline contract end (if no extension) | — | 2026-10-01 | 2026-10-01 | 0 | 0% | Milestone | Oct 1, 2026 — extension strongly recommended per program plan | [7 empty] | ◆
8.2 | Cutover & Close | Decommission | Alation decommission, archive, final audit evidence | Eng / Gov | 2027-09-01 | 2027-10-01 | 4 | 0% | Not started | Align to extended contract Oct 2027
9.0 | Program & Governance | Metrics | Success metrics dashboard — WAU, glossary coverage, search success | Gov / PMO | 2026-06-01 | 2027-04-30 | 47 | 0% | Not started | Steward activity; migration validation summary

## Milestones & KPIs
Key milestones & success criteria (from program documents)
Milestone / KPI | Target / timing | Owner | Detail
Requirements sign-off | May–Jun 2026 | Data Governance | Consolidated requirements; gate before build acceleration.
OMS MVP deployed | Sep–Oct 2026 | OMS / Engineering | Glossary, business search, tags/docs, lineage MVP, usage/ownership where scoped.
Parallel run live | Oct 2026 – Jan 2027 | PMO | Alation + OMS; user validation; lower cutover risk.
Metadata migration validated | Feb 2027 | Engineering / Gov | ≥95% business metadata preserved; lineage & glossary checks.
OMS primary (cutover) | Feb–Mar 2027 | Steering | OMS system of record; Alation read-only.
User adoption | Within 4 wks of cutover | Governance | ≥80% of former Alation WAU active in OMS (product brief target).
Alation decommission | Oct 2027 (extended contract) | Eng / Procurement | Full sunset; archive & audit pack.
Baseline contract date (risk) | 1-Oct-2026 | Sponsor | Without extension: MVP-only + high risk; negotiate extension per project plan.

## Open in Google Sheets
Using this file in Google Drive / Google Sheets
1. Upload | In Google Drive (your program folder), click New → File upload and select this .xlsx, or drag the file into the folder.
2. Open as Sheet | Right-click the file → Open with → Google Sheets. Sheets will convert formatting; review column widths and frozen panes (View → Freeze).
3. Executive view | Hide the month columns you do not need yet, or create a Filter view for leadership with only WBS, Phase, Task, Status, and End date visible.
4. Maintain | Update % Complete and Status weekly; adjust Start/End if dependencies slip. Regenerate from generate_executive_gantt.py if you need a full task reset.
5. Source docs | Aligned to your Product Brief, Migration Project Plan, and appendix timeline (extension scenario to Oct 2027). Milestone 1-Oct-2026 is the baseline contract date.