## Guide
How to use this workbook
1. Start on the Gantt sheet. Columns A–E list workstreams; week columns (Mon-start weeks) show duration bars.
2. Freeze panes are set at the first timeline column — scroll horizontally to see Jul 2026 through fall 2027.
3. Narrow week column width keeps the chart dense; widen column D/E area if you prefer larger date text.
4. Milestones & dates summarizes executive checkpoints; Feature matrix (summary) pulls High MVP items from the inventory doc.
5. To present in PowerPoint: set Gantt zoom ~60–80%, hide gridlines (View), or copy the date range as an image.
Date logic vs. source docs
• Phase 1 requirements = 8 weeks in Jul–Aug 2026; design = 10 weeks ending early Nov 2026; build = 8 months Nov 2026–Jun 2027.
• If your fiscal labels read “Nov–Jun 2027” for development, map that to calendar months Nov 2026–Jun 2027 so launch on 9/16/2027 remains intact.
• Testing = 4 weeks in Jul 2027; migration/UAT/stabilization = 6 weeks after; launch milestone 9/16/2027.

## Gantt
Data Governance — Business Data Catalog Migration (Alation → OMS / In-house)
Sources: Product Brief — Alation to In-house (Mar 2026) · BDC Feature Inventory Matrix (PRD F01–F35). Schedule uses an 8-month build from Nov 2026 through Jun 2027 (so testing, migration, and 9/16/2027 launch stay feasible). Launch target: 9/16/2027 · Mitigate contract risk via extension / parallel run per brief.
Color key — Kickoff ¦ Requirements ¦ Design ¦ Development ¦ Testing ¦ Migration / UAT ¦ Change mgmt ¦ Launch
ID | Phase | Workstream / deliverable | Start | End | 04/27/26 | 05/04/26 | 05/11/26 | 05/18/26 | 05/25/26 | 06/01/26 | 06/08/26 | 06/15/26 | 06/22/26 | 06/29/26 | 07/06/26 | 07/13/26 | 07/20/26 | 07/27/26 | 08/03/26 | 08/10/26 | 08/17/26 | 08/24/26 | 08/31/26 | 09/07/26 | 09/14/26 | 09/21/26 | 09/28/26 | 10/05/26 | 10/12/26 | 10/19/26 | 10/26/26 | 11/02/26 | 11/09/26 | 11/16/26 | 11/23/26 | 11/30/26 | 12/07/26 | 12/14/26 | 12/21/26 | 12/28/26 | 01/04/27 | 01/11/27 | 01/18/27 | 01/25/27 | 02/01/27 | 02/08/27 | 02/15/27 | 02/22/27 | 03/01/27 | 03/08/27 | 03/15/27 | 03/22/27 | 03/29/27 | 04/05/27 | 04/12/27 | 04/19/27 | 04/26/27 | 05/03/27 | 05/10/27 | 05/17/27 | 05/24/27 | 05/31/27 | 06/07/27 | 06/14/27 | 06/21/27 | 06/28/27 | 07/05/27 | 07/12/27 | 07/19/27 | 07/26/27 | 08/02/27 | 08/09/27 | 08/16/27 | 08/23/27 | 08/30/27 | 09/06/27 | 09/13/27 | 09/20/27 | 09/27/27 | 10/04/27 | 10/11/27 | 10/18/27 | 10/25/27
0 | Intake | Kickoff & program intake (T+0 milestone 4/30/26) | 2026-04-27 | 2026-05-08
1 | Phase 1 | Requirements — current use, enhancements, OMS leverage & gaps | 2026-07-01 | 2026-08-25
1a | Phase 1 | Consolidated requirements doc & gate sign-off | 2026-08-18 | 2026-08-28
2 | Design | Solution design — backend (data model, integrations, lineage, APIs) | 2026-08-26 | 2026-10-16
2b | Design | Solution design — frontend / BDC UX (search, glossary, asset IA) | 2026-09-14 | 2026-11-03
2c | Design | Migration design (extract–transform–load, validation strategy) | 2026-10-07 | 2026-11-03
2d | Design | Architecture / design review & approval | 2026-10-27 | 2026-11-03
3 | Build | Development — MVP parity (high-priority catalog: F01–F06, F09–F11, F16, F20–F21, F23–F25, F30, F33) | 2026-11-04 | 2027-03-31
3b | Build | Development — Phase 2 (medium: bulk edit, dataflows, domains, exports, usage, API, policy, etc.) | 2027-01-04 | 2027-06-15
3c | Build | Development — migration tooling, parallel-run hooks, hardening | 2027-04-01 | 2027-06-30
4 | Quality | Test planning, automation & regression prep | 2027-06-01 | 2027-06-30
4b | Quality | Formal testing window (4 weeks, July 2027) | 2027-07-01 | 2027-07-28
5 | Cutover | Migration execution, UAT, stabilization (6 weeks) | 2027-07-29 | 2027-09-11
6 | Adoption | Change management — training, champions, comms calendar | 2027-06-01 | 2027-09-15
6b | Cutover | Go-live readiness, cutover rehearsal, launch | 2027-09-04 | 2027-09-16
7 | Hypercare | Post-launch stabilization (optional window) | 2027-09-16 | 2027-10-16

## Milestones & dates
Milestone | Target date | Notes
Kickoff / intake (T+0) | 2026-04-30 | Program start; align DSS / OMS / stakeholders
Phase 1 requirements complete | 2026-08-28 | 8-week window Jul–Aug 2026 (per plan)
Design complete | 2026-11-03 | 10-week backend + frontend design Aug–Nov
Development window | 2026-11-04 | 8 months through Jun 2027 (MVP → parity → tooling)
Formal testing | 2027-07-01 | 4-week test window (July 2027)
Migration + UAT + stabilization | 2027-07-29 | 6-week execution ending ahead of launch
Launch — Internal Solution primary | 2027-09-16 | Go-live; Alation decommission per contract

## Feature matrix (summary)
BDC Feature Inventory — priority snapshot for migration waves (see full matrix in Google Doc)
# | Feature | Priority | MVP wave | Primary users | PRD
1 | Search & Discovery | High | MVP | DPMs, PMs, Analysts, Stewards | F01
2 | Business Glossary | High | MVP | DPMs, PMs, Analysts, Stewards | F02
3 | Catalog Browse | High | MVP | DPMs, PMs, Analysts, Stewards | F03
4 | Table / asset detail & descriptions | High | MVP | DPMs, PMs, Analysts, Stewards | F04
5 | Recommendations (AI metadata) | High | MVP | Stewards | F16
6 | Flags (endorse / warn / deprecate) | High | MVP | DPMs, PMs, Analysts, Stewards | F21
7 | Data Lineage | High | MVP | DPMs, Engineers, … | F05
8 | Admin analytics dashboard | High | MVP | Admin | F25
9 | Tags & classification | High | MVP | Governance, DPMs, Stewards | F06
10 | Expanded data sources | High | MVP | Admins | F30
11 | Product pages (authoring) | High | MVP | PMs, DPMs, Stewards | F33
12 | Data sources & connectors | High | MVP | DPMs, Engineers | F11
13 | Authentication / SSO | High | MVP | All users | F20
14 | Folders / source navigation | High | MVP | Cross-functional | F23
15 | Ownership / stewardship | High | MVP | Admin | F09
Medium / Phase 2 examples | Bulk edit, dataflows, domains, exports, usage metrics, AI chat, catalog sets, dictionary import/export, saved queries, overview & social, custom fields, comments, version control, policy center, …